## Summary Budget
Actual costs based on Detailed Budget
Activity/Budget Item | Partner | Total (rough numbers) | Percent | Design Phase | Scale Phase
Salaries and Fringe Benefits | Dimagi | 425000 | 41.34% | 250256.004 | 175162.992
Travel | Dimagi | 15000 | 1.459% | 7600 | 7600
User Accaptability Testing | LLO | 40000 | 3.891% | 40000
Mother Baby Welness Delivery - LLO | LLO | 438000 | 42.61% | 18000 | 420000
Mother Baby Welness Delivery - Dimagi | Dimagi | 110000 | 10.7% | 4500 | 105000
Total |  | 1028000 | 58.66% | 320356.004 | 707762.992 | 1028118.996
Share of budget for Dimagi | 53.5%
Share of budget for LLOs | 46.49%

## Timeline (for proposal)
|  |  | Scale Phase Timeline (Months) | [12 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Phase | Activities | Target | Design phase timeline | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Design - build | Consult experts to design content and intervention |  | 2024-01-02 | bar: 1 to 4
| Build Learn and Deliver applications (iteratively, while testing) |  | 2024-02-05 | bar: 2 to 6
| Iterative Learn experiments with NM to validate digital learning tool |  | 2024-03-05 | bar: 3 to 6
| Iterative pilot cohorts to validate LDVP |  | 2024-06-08 | bar: 5 to 8
Design - test | Full 5-6 month cohort | 2,000 mothers reached | 2024-09-14 | bar: 9 to 2 14
| Document analysis & learnings from design phase |  | 2024-12-15 | bar: 12 to 3 15
Scale | Establish contracts with scale phase partners | LLOs in 3 countries | 13-15 / 1-3 of scale phase | bar: 1 13 to 3 15
| Permissions and other preparations by LLOs |  | 2024-04-05 | bar: 4 16 to 5 17
| Application and implementation readiness by Dimagi for scale pilot |  | 2024-04-05 | bar: 4 16 to 5 17
| LLOs register new FLWs in monthly cohorts (increasing in scale) | 35,000 mothers reached | 2024-06-12 | bar: 6 18 to 12 24
| FLWs register new mothers |  | 2024-06-14 | bar: 6 18 to 14 26
| FLWs conduct visits with mothers |  | 2024-06-18 | bar: 6 18 to 18 30
| Document analysis & learnings from scale phase |  | 15-18 | bar: 16 28 to 18 30
Scale estimates
OPTION 2 WITH MORE SCALE COHORTS AND MORE OVERLAP | bar: 1 to 18 30
Scale - option 2 | Establish contracts with scale phase partners | LLOs in 3 countries | 13-15 / 1-3 of scale phase | bar: 1 13 to 3 15
| Permissions and other preparations by LLOs |  | 4 | bar: 4 16
| Application and implementation readiness by Dimagi for scale pilot |  | 4 | bar: 1 13 to 4 16
| Pilots (3 countries, 7 months each) | 150 FLWs or 3,000 mothers | 2024-05-11 | bar: 5 17 to 11 23
| Scale phase 2 | 500 FLWs or 10,000 mothers | 2024-08-10 | bar: 8 20 to 15 27
| Scale phase 3 | 1,000 FLWs or 20,000 mothers | 2024-11-18 | bar: 11 23 to 18 30
| Document analysis & learnings from scale phase | N/A | 16-18 | bar: 16 28 to 18 30
OPTION 3 - STARTS AT MONTH 16, ENDS ON MONTH 30 (same number of cohorts as option 1) | bar: 1 to 18 30
Scale (option 3) | Establish contracts with scale phase partners | LLOs in 3 countries | 1-3 (mo 16-18 of cumulative timeline) | bar: 4 16 to 6 18
| Permissions and other preparations by LLOs |  | 4 | bar: 7 19
| Application and implementation readiness by Dimagi for scale pilot |  | 4 | bar: 4 16 to 7 19
| Pilots (3 countries, 7 months each) | 500 FLWs or 10,000 mothers | 2024-05-11 | bar: 8 20 to 14 26
| Scale preparations |  | 2024-08-10 | bar: 9 21 to 10 22
| Scale (3 countries, 8 months each) | 1,150 FLWs or 23,000 mothers | 2024-11-18 | bar: 11 23 to 18 30
| Document analysis & learnings from scale phase | N/A | 16-18 | bar: 16 28 to 18 30