## Sheet1
| 2024 | 2025 | [11 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028
| Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Pilot Phase' - 30 GVHs
Cash transfers (first cohort) | bar: 2025 Feb
Cash transfers (remaining cohorts) | bar: 2025 Mar to 2025 Aug
Data collection
Market & Village scoping | bar: 2024 Dec
Household census (first cohort) | bar: 2025 Jan
Household surveys (first cohort) | bar: 2025 Feb; 2025 May; 2025 Aug; 2025 Nov; 2026 Jun; 2026 Dec
Household census (remaining cohorts) | bar: 2025 Feb to 2025 Jul
Household surveys (remaining cohors) | bar: 2025 Mar to 2026 May; 2026 Jul to 2027 Jun
Market census (monthly) | bar: 2025 Jan to 2025 Dec; 2026 Mar; 2026 Jun; 2026 Sep; 2026 Dec
Price surveys (monthly) | bar: 2025 Jan to 2025 Dec; 2026 Mar; 2026 Jun; 2026 Sep; 2026 Dec
Enterprise surveys, markets (monthly) | bar: 2025 Jan to 2025 Dec; 2026 Mar; 2026 Jun; 2026 Sep; 2026 Dec
Analysis
Short-term price effects (up to 6m) | bar: 2025 Sep to 2026 Sep
Short-term expenditure and market activity effects (6m) | bar: 2025 Sep to 2026 Sep
1-year Endline HH and political impacts | bar: 2026 Jan to 2027 Jan
2-year Endline HH impacts | bar: 2027 Jan to 2028 Jan
Scale-Up Phase' - 100+ GVHs
Cash transfers (first cohort) | bar: 2025 Oct
Cash transfers (remaining cohorts) | bar: 2025 Nov to 2026 Sep
Data collection
Market census (monthly) | bar: 2025 Aug to 2027 Oct
Price surveys (monthly) | bar: 2025 Aug to 2027 Oct
Enterprise surveys, markets (monthly) | bar: 2025 Aug; 2025 Oct; 2025 Dec; 2026 Feb; 2026 Apr; 2026 Jun; 2026 Aug; 2026 Oct; 2026 Dec; 2027 Feb; 2027 Apr; 2027 Jun; 2027 Aug; 2027 Oct
Household & village enterprise census (first cohort) | bar: 2025 Aug; 2027 Sep
Household & village enterprise surveys (first cohort) | bar: 2025 Sep; 2026 Jan; 2026 Apr; 2026 Jul; 2026 Oct; 2027 Oct
Household census (remaining cohorts) | bar: 2025 Sep to 2026 Jul
Household surveys - baseline (remaining cohors) | bar: 2025 Oct to 2026 Aug
Household surveys - midline (remaining cohors) | bar: 2026 Feb to 2027 Jun
Household surveys - 1-year endline (remaining cohors) | bar: 2026 Nov to 2027 Sep
Household surveys - 2-year endline (remaining cohors) | bar: 2027 Nov to 2028 Sep
Analysis
Short-term price effects (up to 12m) | bar: 2026 Apr to 2027 Nov
Short-term expenditure and market activity effects (6m) | bar: 2026 Apr to 2027 Nov
1-year Endline HH and political impacts | bar: 2026 Aug to 2028 Feb
2-year Endline HH impacts | bar: 2027 Aug to 2028 Dec